## excel
/Non Project/PSP Fundamentals & Advanced/Program 4
PSP2 Project Plan Summary
Project Settings
Project Owner | Juan Pablo Ospino Solano
Start Date | mar 20, 2017 07:11:08 AM
Completion Date | mar 21, 2017 10:08:02 PM |  |  |  | Completed: *
Keywords
Language | Java
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 22.1 | 42.6 | 29.7
Planned Time | 0.12222 |  | 0.95069
Actual Tiempo |  | 0.14097 | 1899-12-31 02:54
CPI (Cost-Performance Index) |  |  | 0.85
% Reuse | 0% | 0% | 2.09%
% New Reusable | 0% | 0% | 7.26%
Test Defects/KLOC or equivalent | 1.53 | 0 | 1.25
Total Defects/KLOC or equivalent | 15.3 | 13.9 | 15
Yield % | 80% | 100% | 83.3%
Code Review Rate | 1638 | 2880 | 2179
Program Size
| Plan | Actual | A la Fecha
Base (B) | 0 | 0 | 0
Deleted (D) | 0 | 0 | 0
Modified (M) | 0 | 0 | 0
Added (A) | 64.7 | 144 | 799
Reused (R) | 0 | 0 | 11
Added and Modified (A+M) | 64.7 | 144 | 799
Total Size (T) | 64.7 | 144 | 526
Total New Reusable | 0 | 0 | 58
Estimated Proxy Size (E) | 73 | 12 | 413
Time In Phase
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.015278 | 0.029167 | 0.15347 | 13.7%
DiseÃ±o | 0.0041667 | 0.0020833 | 0.038194 | 3.41%
RevisiÃ³n de DiseÃ±o | 0.00069444 | 0.0013889 | 0.0090278 | 0.81%
CodificaciÃ³n | 0.085417 | 0.077083 | 0.75903 | 67.7%
RevisiÃ³n de CodificaciÃ³n | 0.0013889 | 0.0020833 | 0.015278 | 1.36%
CompilaciÃ³n | 0.0027778 | 0.00069444 | 0.020833 | 1.86%
Pruebas | 0.0027778 | 0.0097222 | 0.03125 | 2.79%
Postmortem | 0.0090278 | 0.01875 | 0.09375 | 8.36%
Total | 0.12222 | 0.14097 | 1899-12-31 02:54
Defects Injected
| Plan | Actual | A la Fecha | % A la Fecha
Antes de Desarrollo | 0 | 0 | 0 | 0%
PlaneaciÃ³n | 0 | 0 | 0 | 0%
DiseÃ±o | 0.4 | 0 | 4 | 33.3%
RevisiÃ³n de DiseÃ±o | 0 | 0 | 0 | 0%
CodificaciÃ³n | 0.59 | 2 | 8 | 66.7%
RevisiÃ³n de CodificaciÃ³n | 0 | 0 | 0 | 0%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0 | 0 | 0 | 0%
Total | 0.99 | 2 | 12
Defects Removed
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0 | 0 | 0 | 0%
DiseÃ±o | 0 | 0 | 0 | 0%
RevisiÃ³n de DiseÃ±o | 0.1 | 0 | 1 | 8.33%
CodificaciÃ³n | 0.69 | 0 | 7 | 58.3%
RevisiÃ³n de CodificaciÃ³n | 0 | 2 | 2 | 16.7%
CompilaciÃ³n | 0.1 | 0 | 1 | 8.33%
Pruebas | 0.1 | 0 | 1 | 8.33%
Total | 0.99 | 2 | 12
After Development | 0 | 0 | 6
Defect Removal Efficiency
| Plan | Actual | A la Fecha
Defects/Hour - Design Review | 4.32 | 0 | 4.62
Defects/Hour - Code Review | 0 | 40 | 5.45
Defects/Hour - Compile | 1.64 | 0 | 2
Defects/Hour - Test | 1.53 | 0 | 1.33
DRL (DLDR/UT) | 2.82 | 0 | 3.46
DRL (Code Review/UT) | 0 | 30 | 4.09
DRL (Compile/UT) | 1.07 | 0 | 1.5
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 10:08 PM el 21/03/2017